## Vulnerability Master Tracker
Category | Vulnerability Name | Severity | Vulnerability Description & Impact | Client Recommendation | Moody's / Vendor Response | Client Rebuttal / Notes | Status
Authentication & Session | Default Admin Credentials | High | System utilizes default, predictable administrative credentials (admin/admin). Risk of complete system compromise and data exfiltration. | Mandate password change on initial login, remove default accounts, enforce MFA. | Password updated on all environments. | Accepted and verified. | Resolved
Authentication & Session | Lack of Rate Limiting & Brute Force Protection | Medium | Login authentication endpoint lacks rate-limiting and account lockout controls; CAPTCHA mechanism can be bypassed via automated tools (Burp Intruder). | Enforce strict rate-limiting (max 5 failed attempts), account lockout, and robust server-side CAPTCHA validation. | Captcha can be enabled in Admin -> Access Control. Captcha expiration (captchaExpiration) added in CL 25.31+. Rate limiting enforced at WAF level. | WAF rate limiting must be configured by client infrastructure team. Captcha enabled for local accounts. | Addressed / Configured
Authentication & Session | Session Hijacking (Token Reuse) | High | Valid authenticated session cookies could be reused or injected into another browser/session without re-authentication. | Implement secure session management, rotation after login, device/IP validation, and secure cookie attributes. | This is not a valid finding. Copying the token from browser with a valid session is not session hijacking. Client-side info can be tempered. | Disputed by vendor. Client notes token exposure risks remain if not properly bound. | Disputed / Accepted Risk
Authentication & Session | Unencrypted Login Request | High | Sensitive authentication parameters/credentials passed unencrypted or vulnerable to interception. | Ensure all sensitive input and login requests are sent encrypted via strong TLS (TLS 1.2+). | TLS configuration and certificate management are managed by the customer for on-premise installations. | Customer responsibility. Ensure minimum SHA256 and TLS 1.2+. | Customer Action Required
Injection & Scripting | Stored Cross-Site Scripting (Stored XSS) | High | Improper sanitization of user-supplied input (Display Name, First Name, etc.) allows arbitrary JavaScript/SVG execution in user browsers. | Implement strict server-side input validation, contextual output encoding, and CSP controls. | Confirmed. Engineering is working on a fix. Expected release in CreditLens 26.31. | Requested ETA and documented remediation plan. Vendor does not share internal implementation details. | In Progress (CL 26.31)
Injection & Scripting | HTML Injection | Medium | User-controlled HTML content rendered directly without neutralization, risking phishing or session compromise. | Implement strict input validation, output encoding, and filter dangerous HTML tags/event handlers. | Sub-item of XSS finding. Fix is already being worked internally, scheduled for CreditLens 26.31. | Tracked alongside Stored XSS fix. | In Progress (CL 26.31)
Security Headers & CSP | Missing Security Headers / CSP / CORP / COOP / COEP | Low | Missing Content-Security-Policy (CSP), COEP, COOP, CORP, and Permissions-Policy headers leaving application vulnerable to cross-origin attacks. | Implement robust CSP restricting script execution and set secure Cross-Origin isolation headers. | For on-premise deployments, HTTP security headers are configured at the server/infrastructure layer by the customer. CSP present in some modules with unsafe-inline/eval required for functionality. | Clarify impact on third-party integrations (Walkme, Vimeo, Qualtrics). Set explicit object-src 'none'. | Customer Configuration / Partially Addressed
Configuration & Secrets | Hardcoded Secrets / Google API Key Exposure | Medium / Low | Functional Google API Key embedded directly within client-side JavaScript code/assets, risking quota exhaustion and unauthorized usage. | Revoke/rotate exposed keys, apply application/API restrictions in GCP Console, and proxy requests through backend. | This is expected behavior. Google Maps runs client-side and requires the API key in the browser to function. | Requires strict referrer and API restrictions in Google Cloud Console to prevent abuse. | Accepted Risk / Secured via GCP Restrictions
Configuration & Secrets | Database Connection String Exposure | Low | Backend PostgreSQL connection strings and internal configuration details exposed via `/api/config/tenants` endpoint. | Remove sensitive configuration details and credentials from client-facing API responses. | The endpoint was restricted in CreditLens 25.31 and is no longer present in 26.11. | Verified fixed in recent versions. | Resolved
Configuration & Secrets | Cookie Domain & Attribute Misconfiguration | Medium / Low | Authentication/session cookies issued with insecure domain (`test.com`) or missing `Secure` / `SameSite` attributes. | Configure strictly scoped domain attributes and enforce `Secure`, `HttpOnly`, and `SameSite=Strict/Lax`. | Cookie domain is configured during deployment. Vendor investigating as behavior could not be replicated. | Ensure deployment templates enforce Secure and SameSite attributes correctly. | Under Investigation
Dependencies | Vulnerable & Outdated JavaScript Library (Bootstrap v3.4.1) | Medium / Low | Application uses EOL version of Bootstrap (v3.4.1) containing known vulnerabilities (e.g., CVE-2024-6485, CVE-2019-8331). | Upgrade Bootstrap to supported version (v5.3.x+) or remove unused vulnerable components. | Bootstrap is part of legacy UI; planned for future removal. Vulnerabilities do not impact CreditLens as vulnerable components are never used. | Accepted risk due to non-utilization of vulnerable components, but long-term removal requested. | Accepted Risk / Legacy
Information Disclosure | Hidden Directories Detected | Low | Server exposes internal or test directory structures (e.g., `/aux/`, `/com1/`) responding with 200/403 status codes. | Remove unused resources or return 404 Not Found status instead of 403 Forbidden. | Reported paths do not represent hidden or accessible application directories (standard resources or invalid paths). | Noted and closed. | Closed / False Positive